## Sheet1
*Annual Procurement Plan For the Year 2025 (Under Rule 8 and 9 of the Public Procurement Rules 2004) Name of Agency: National Bank of Pakistan (Digital Banking Group-2025) | [7 empty] | 320 | USD Rate
Sr. No | Name of Procurement (Description) | Estimated Cost (PKR) | **Procurement Method | Tentative Date of Procurement Notice Publication | Tentative Date of Award of Contract | Tentative Date of Completion | Remarks (if any)
1 | LOS System Procurement | 704000000 | Open Competitive Bidding | Q1-2025 | Q2-2025 | Q2-2026
2 | Redesigning & Revamping of NBP Website | 16000000 | Open Competitive Bidding | Q1-2025 | Q2-2025 | Q4-2025
3 | Digital Supply Chain Financing | 24960000 | Open Competitive Bidding/Farmework Agreements | Q1-2025 | Q1-2025 | Q2-2025
4 | LOS Hardware | 240000000 | Open Competitive Bidding | Q3-2025 | Q4-2025 | Q1-2026
5 | Digital Research & Development and Proof of concept initiaitives | 64000000 | Open Competitive Bidding | Q2-2025 | Q3-2025 | Q4-2025
6 | Digital Wallet | 320000000 | Open Competitive Bidding | Q1-2025 | Q2-2025 | Q3-2025
7 | NBP Digital Employee Intranet | 80000000 | Open Competitive Bidding | Q2-2025 | Q3-2025 | Q4-2025
8 | Data Transformation Projects (Data architecture & projects) | 320000000 | Open Competitive Bidding | Q2-2025 | Q3-2025 | Q4-2025
9 | Enterprise Data warehouse | 160000000 | Open Competitive Bidding | Q3-2025 | Q4-2025 | Q1-2026
10 | Merchant Acquiring Solution | 100000000 | Open Competitive Bidding | Q3-2025 | Q4-2025 | Q1-2026
11 | ATM Machines (Procurement With Installation) - 200 Unit (200) | 800000000 | Open Competitive Bidding | Q1-2025 | Q2-2025 | Q3-2025
12 | CCDM/CDM - 50 Units | 240000000 | Open Competitive Bidding | Q1-2025 | Q2-2025 | Q3-2025
*The Annual Procurement Plan may be prepared on the assumption that total allocated budget will be released.
**Procurement method means Open Competitive Bidding / Petty Purchases / Quotations / Direct Contracting / Negotiated Tedering.
(Please add additional sheets if required)
| Sohail Malik |  |  | Adnan Nasir- GC DBG